## IMS - Risk Assessment
Risks |  |  | Initial Risk Level |  |  | Response |  | Risk Level aftter Control Measures |  |  | Final Review
Risk ID | Cause | Effect | Likelihood | Severity | Overall Risk Level | Strategy | Control Measures | Likelihood | Severity | Overall Risk Level
1 | Minimum Viable Product not delivered | Developer is still undergoing training and has a limited programming experience. The code may not execute desired functions. Therefore unable to deliver an MVP. | 3 | 5 | 15 | Mitigate | Developer should use the courseware and the trainers help if any issues arise. | 1 | 5 | 5
2 | Product does not meet the minimum requirments | Not reading the project specification thoroughly and not prioritising the feautures to deliver the MVP. | 1 | 5 | 5 | Mitigate | Carefully read the project specificition and create user stories for all required features for the MVP. | 1 | 1 | 1
3 | Poor time management | First projet for developer so not aware of how long a task would take. This results in not enough time planned to complete tasks in a timely manner. This will put the project at risk of incompletion. | 3 | 5 | 15 | Mitigate | Use sprints to complete tasks specified within user stories. Setting smaller deadlines for feautures throughout the project. This would help in better progress tracking and time management. | 1 | 5 | 5
4 | Loss of Wifi connection | Wifi connection issues may arise as currently there are broadband blackouts in the area, this would prevent any offline work from being updated on the repository also leading to incomplete version control on github. | 3 | 5 | 15 | Avoid | Find a place with stable connection and conduct work for the week at this location to avoid the possibility of a connection loss all together. | 1 | 1 | 1
5 | Unplanned absence | Absence due to unforseen circumstances such as illness, could prevent the completion of the project | 2 | 4 | 8 | Accept | Absence due to unforseen illness can not be planned for. The developer should inform the trainer as soon as possible so that adjustments can be made accordingly. | 2 | 4 | 8
6 | Hardware Failure | Current laptop is 5 years old and possibility of a crash is higher than normal. This would mean total data loss for the project and any progress along with it. | 4 | 5 | 20 | Mitigate | Make sure the laptop is updated and meets the minimum requirement to run the softwares required. Use git and github to continuosly integrate work by pushing feature branches to dev branch frequently. So even if the laptop does crash there is backup of the source code in the repository. | 2 | 1 | 2
7 | Product fails to meet 80% testing coverage | Developer is new to testing and most of the syntax is new as it was not covered in the training. Would take longer than normal to understand and utilise the code which will increase the time required for testing. | 3 | 5 | 15 | Mitigate | Developer should use the courseware and the trainers help if any issues arise. Look into testing outside of working hours to get familiar with the syntax used for testing. | 2 | 2 | 4
8 | Extreme Weather Warning - Heatwave | Could be hospitalised due to the heatwave. Resulting in project not being completed. | 1 | 5 | 5 | Mitigate | Regular breaks from work and stay well hydrated to prevent exhuastation and dehydartion. | 1 | 1 | 1

## Risk Matrix
Severity | 5 | 5 | 10 | 15 | 20 | 25
| 4 | 4 | 8 | 12 | 16 | 20
| 3 | 3 | 6 | 9 | 12 | 15
| 2 | 2 | 4 | 6 | 8 | 10
| 1 | 1 | 2 | 3 | 4 | 5
|  | 1 | 2 | 3 | 4 | 5
Likelihood